## Slide 1: امکان سنجی طرح کسب و کار
دکتر علی خوزین

## Slide 2: 4 مرحله قبل از ایجاد کسب و کار
1- شناسایی ایده ها و امکانات
2- مطالعات فنی و اقتصادی مقدماتی
3- مطالعات فنی و اقتصادی نهایی
4- ارزیابی نهایی و تصمیم گیری

## Slide 3: 1- شناسایی ایده ها و امکانات سرمایه گذاری
-شامل منابع طبیعی -الگوهای تولیدی و کشاورزی
-روندهای تقاضا کالای مصرفی -رشد جمعیت
-وضعیت واردات و صادرات -تولید داخلی
-زمینه های صنعتی -نیروی کار
-منابع تامین سرمایه بالفعل و بالقوه
-سایر عوامل زیربنایی -وجود حلقه های زنجیره تولید
-پیشینه های صنعتی -امکان رشد و گسترش تولید

## Slide 4: 2- مطالعات فنی و اقتصادی مقدماتی
اهداف و لزوم اجرای طرح
معرفی محصول و موارد مصرف
بررسی اجمالی بازار
بررسی محل مناسب
نحوه تکمیل تکنولوژی
تعداد پرسنل مورد نیاز
برآورد امکانات زیربنایی، زمین، تاسیسات و ..
برق، سوخت، آب و ...
برآورد سرمایه ثابت و سرمایه در گردش مورد نیاز
شاخص های اقتصادی و مالی

## Slide 5: 2- مطالعات فنی و اقتصادی مقدماتی
؟
دورنمای مناسب (اقدام برای ایجاد کسب و کار)
دورنمای نامناسب (عدم ایجاد کسب و کار)
وجود ابهام
نیاز به تحلیل جامع در نقاط حساس

## Slide 6: 3- مطالعات فنی و اقتصادی نهایی
زوایای مبهم و ناشناخته فنی، اقتصادی، قانونی و ..
اهداف و علل انتخاب طرح، حجم بازار، ظرفیت، برنامه تولید، تکنولوژی مطلوب
مواد اولیه، سایر ورودیها، کیفیت و کمیت نیروی انسانی، سازمان و تشکیلات
ساختار هزینه، برنامه آموزش، هزینه سرمایه گذاریها و بهربرداری، تحلیل حساسیت

## Slide 7: 3- مطالعات فنی و اقتصادی نهایی
5. محدوده کسب و کار (تمام فعالیتهایی که قرار است در کسب و کار انجام شود-خدمات، تولید، فروش، توزیع، تحقیق و توسعه و ...)
6. SWOT ، اهداف، تاریخچه، بازارها، ظرفیت، مطالعات تکنولوزیک
ظرفیت
........

## Slide 8
ظرفیت
ظرفیت اسمی: توسط سازنده تعیین و در شرایط ایده آل و تئوریک قابل دستیابی است
واقعی: در عمل قابل دستیابی است. بر اساس تقاضای بازار، شرایط سالهای قبل و در شرایط عادی
عملی: توسط مهندسین و در سطح مشخصی از کارایی قابل دستیابی است.

## Slide 9
انتخاب محل کارخانه
نیروی کار
دسترسی به بازار مصرف
امکان دسترسی به مواد اولیه
الزامات
سایر موارد
تاسیسات زیربنایی
شرایط جغرافیایی
راه ها
سوابق صنعتی محلی
مسائل مالی و اقتصادی
...

## Slide 10
4- ارزیابی نهایی و تصمیم گیری

## Slide 11: What is a Feasibility Study
Is this a good business idea?
Helps answer the question of whether to go forward with the business idea.

## Slide 12: What is a Feasibility Study
A feasibility study is valuable for:
Starting a new business
Expansion of an existing business
Adding an enterprise to an existing business
Purchasing an existing business

## Slide 13: What is a Feasibility Study
A feasible business will:
Generate adequate cash flow and profits,
Withstand risks,
Remain viable in the long-term
Meet the goals of the founders

## Slide 14: What is a Feasibility Study
Evaluate Alternatives
The feasibility study helps to “frame” and “flesh-out” specific business scenarios so they can be studied in-depth.

## Slide 15: What is a Feasibility Study
Pre-Feasibility Study
May help sort our alternatives and determine if a full-blown feasibility study is warranted.

## Slide 16: What is a Feasibility Study
Market Assessment
A market assessment may be conducted first to identify market opportunities. If no opportunities exist, there may be no reason to proceed further.

## Slide 17: What is a Feasibility Study
Study Results
Outline in depth the various business scenarios examined and the implications, strengths and weaknesses of each.

## Slide 18: What is a Feasibility Study
Go/No Go Decision
The feasibility study will be a major information source in making this critical decision.

## Slide 19: Reasons Not to do a Study
We already know it is feasible.
We did a study a couple of years ago.
Just a way for consultants to make money.
The company selling us the equipment says it is feasible.
Lets hire a general manager and have him do the study.
Waste of time – we need to buy the site and begin construction.

## Slide 20: Reasons to Do a Study
Gives focus to the project.
Narrows the business alternatives.
Identifies new opportunities.
Identifies reasons not to proceed.
Provides valuable information for “go/no go” decision.
Increases probability of business success by identifying weaknesses early.

## Slide 21: Reasons to Do a Study
Provides documentation that the idea was thoroughly investigated.
Helps attract funding from lenders, grant providers, etc.
Helps attract equity investment

## Slide 22: Not the Business Plan
Feasibility study conducted before decision to proceed (go/no go).
Business plan prepared after decision to proceed (go/no go).
Feasibility study provides investigative function.
Business plan provides planning function.

## Slide 23: Feasibility Study Outline
1) Description of the Process:
Identification and exploration of business scenarios.
Define the project and alternative scenarios.
Relationship to the surrounding geographical area.

## Slide 24: Feasibility Study Outline
2) Market Feasibility
Industry description.
Industry competitiveness.
Market potential
Access to market outlets.
Sales projection

## Slide 25: Feasibility Study Outline
3) Technical Feasibility
Determine facility needs.
Suitability of production technology.
Availability and suitable of site.
Raw materials.
Other inputs.

## Slide 26: Feasibility Study Outline
4) Financial/Economic Feasibility
Estimate the total capital requirements.
Estimate equity and credit needs.
Budget expected costs and returns.

## Slide 27: Feasibility Study Outline
5) Organizational/Managerial Feasibility
Business Structure
Business Founders

## Slide 28: Feasibility Study Outline
Study Results
Identify and describe various business scenarios.
Compare and contrast scenarios.
Outline criteria for decision making.

## Slide 29: When to Do & How to Use
When to do a Study?
Who will do the Analysis?
How will you Monitor the Study Progress?
How to Accept or Reject the Study?
How to Use the Results?